|  |  |  |  |
| --- | --- | --- | --- |
| ACTIVITY | PREDECESSOR | DURATION | RESOURCES |
| A1 | - | 4d | 2 Analysts, 1 Con.Eng. |
| A2 | A1 | 2d | 3 Analysts, 1 Developer, 1 Con. Eng., 1 Designer |
| A3 | A2 | 2d | 2 Analysts |
| B1 | A3 | 5d | 2 Designers |
| B2 | B1 | 6d | 2 Designers |
| B3 | B2 | 3d | 1 Designer & 1 Analyst |
| B4 | B2 | 7d (1w) | 2 Designers & 1 Analyst |
| C1 | A3 | 12d (1w 5d) | 3 Developers |
| C2 | C1 | 7d (1w) | 2 Developers & 1 Analyst |
| C3 | C2 | 3d | 1 Developer & 1 Con.Eng. |
| D1 | C1 | 8d (1w 1d) | 2 Con.Eng.& 1 Dev. & 1Anal. |
| D2 | D1 | 6d | 1 Con.Eng. & 1 Developer |
| D3 | D2 | 3d | 1 Control Engineer |
| E1 | B3, B4, C3, D3 | 1d | 1 Developer |
| E2 | B3, B4, C3, D3 | 15d (2w 1d) | 1 Analyst & 1 Con.Eng. |
| F1 | E1 | 9d (1w 2d) | 2 Analysts |
| F2 | E1 | 9d (1w 2d) | 2 Analysts |